## Sheet1
Group | Task | Responsible Position | July | August | September | October | November | December | January | February | March | April | May | June
Scheduling
| Develop master schedule for the year | Scheduler
| Develop list of Board Meeting Dates | Scheduler
| Contact City for use of Garrison Gym | Scheduler
| Contact City for use of Shaws Lane | Scheduler
| Concatct Ice Arena for use of facility | Scheduler
| Coordinate with other towns for Interleague Scheduling meeting | Scheduler
| Host interleague scheduling meeting | Scheduler
| Verify interleague schedules with other towns websites | Scheduler
| Coordinate with high school for use of Shaws Lane | Scheduler
| Develop Indoor schedule | Scheduler
| Develop and input 6U, 8U, 10U, 12U, 16U schedules (verfiy conflicts in advance) | Scheduler
| Develop schedule for Opening Day | Scheduler
| Team Formation - set date and reserve location | Scheduler
Sponsorship and Fundraising
Develop sponsorship letter
Send Sponsorship letter
Sponsor letter follow-up meetings
Purchase any new sponsorship signs
Hang sponsorship signs
Print Cash Calendars
Develop list of cash calendar purchases to hand out calendars
Coaching
Spring Coaching Applications/Approvals
Set up 2017 background check on SI Play
Coordinate NH Coach Smart training with Rec for new coaches
Verify all coaches have a valid background check
Summer Coaching Applications/Approvals
Coaches attend team formation
Coaches reach out to team
Practices and games
Coordinate assigning keys to coaches (South Side Only)
Corrdinate collecting keys from coaches (South Side Only)
Train new coaches on operating the four wheeler (South Side Only)
Field Maintenance
Coordinate Spring Field Clean-up (Shaws and South Side)
1. Hang Sponsor Signs and dugout signs - need zip ties
2. heavy drag, mat drag and rake infields
3. Pick up trash, leaves, etc.
4. Rake gardens
5. Batting cage rough rake and smooth
6. Hang batter screen behind home plates at South Side
7. Hang batting cage
8. Clear all fence lines of trash and leaves
9. Weed wack all fence lines
10. Clean and organize concession stand
11. Clean and organize storage closets
12. Clean dugouts
13. Test Scoreboards
14. Walk entire fields looking for sticks, stones, dog poop
15. Paint foul lines
16. check bathrooms and clean if necessary
17. check field liner to make sure it works
18. check fields to see if any edging and/or filling required (especially on deck circles)
Purchase and deliver field lime and turface
Arrange for town to turn on water at South Side
Arrange for porta-potty deliveries and cleaning
Arrange Waste Management to empty dumpster
Purchase and deliver field paint
Coordinate Fall Field Closure (Shaws and South Side)
1. Remove and put away Sponsor Signs and dugout signs
2. heavy drag infields
3. Remove batting cages and put away
4. Remove batter screens behind home plate and put away
5. Empty trash cans and put them away
6. Clean and organize concession stand
7. Clean and organize storage closets
8. Clean dugouts
9. Put trash cans away
10. Secure all valuable items (PA system, scoreboard controller, etc.)
11. Coordinate with City to turn off water
12. turn off and drain hot water tank at South Side
13. Coordinate dumpster to be emptied
14. Coordinate the removal of porta-potties at South Side
Treasurer
Develop annual budget for consideration
Develop monthly profit/loss statement for board meetings
Payment of outstanding invoices
Ensure checks are at fields for umpires before the games
Select and pay calendar Winners
Ensure enough cash/change is in the concession stands prior to first games
Registration
Update Registration and open registration for spring
Coordinate with Rec Department for Spring Sign-up
Coordinate Volunteers for February and March in-person registration
Assign players to teams based upon team formation
Player Rosters and fees to the Rec Department
Develop rosters and paperwork for Summer Teams
Website
Prepare website for registration
Manage website updates
Communicate to inquiries
Umpiring
Contact umpires and assign to games
Assessments and Team Formation
Secure facility to hold the assessments
Communicate assessment schedule with parents
Develop scoring sheets for coaches use during assessments
Coordinate assessments
Secure facility to hold the team formation meeting
Summarize scoring and rank players
Coordinate team formation meeting
Communicate team assignments to registrar to enter into the system
Board
Nominate new Board members
Vote in new Board members
Review and upate League Bylaws
Coaching Approvals (Spring and Summer)
Obtain Babe Ruth Insurance for the year
Obtain South Side Insurance for the year
Coordinage Heyliger Award and Sponsor of the Year recipient
Attend President's meeting with Red Department
Attend State Babe Ruth meeting
Secretary
Document and distribute meeting agenda
Document and distribute meeting minutes
Opening Day
Concession Volunteers
Set up gas grill and propane tanks
Reserve and set up bounce houses and games
Schedule of events
Email concession donations by league
Reserve DJ
Reserve National Anthem Singer
Communicate Opening Day schedule to parents
Set up tables, chairs, tent
Team Pictures - arrange for photographer
Purchase medals for skills competition
Agenda for day including: oldest/youngest, list of sponsors, speakers, board members, etc.
Coordinate Varsity/JV/Reserve teams
Field preparation
Clean-up and put everything away
Ensure enough cash/change is in the concession stand
Concession
Clean concession stands
Purchase food/drink and stock concession stand
Send email to families for concession stand donations
Develop and send schedule for volunteers
Communicate schedule with coaches and division directors
Ensure cash/change is in the cash drawers
Evaluate stock for concession stands - weekly
Empty Shaws concession and clean
Empty South Side concession and clean
End of Year Banquet
Order championship trophies and T-shirts
Order medals
Communicate and coordinate Event
Equipment/Uniforms
Inventory Equipment Bags, Prepare lists of items to purchase for followin season
Inventory all softballs (hard, soft, 6U teeballs), prepare lists of balls for purhcase following yr
Inspeact all training equipement, Prepare list for purhcase next year
Inventory all Coaches Apparel, prepare order for next year
prepare budget for next year
submit coach apparel order to collins
place orders for replacement equipment/balls to ensure it arrives by March
Inventory and replenish all first aid kits
prepare equip bags for coach handout
equipment handout, coach appareall handout
ensure all T's, batting nets, portable bases are all in good working order and in proper storage
Fit entire league of uniforms for shirts, pants, visors, and socks
order uniforms, need them the week before opening day typically first Sat in May
pick up uniforms and spread out all over your house to package for each team w coaches gear
distribute uniforms to each team or put in central location for each to pick up
prepare/distribute summer team equip bags BABE RUTH TEAMS ONLY
order 10u/12u/16u Championship shirts for players and coaches, hope to have for banquet
get all spring bags/batting helmets/first aid kits back from coaches at end of year banquet
get all Babe Ruth Summer team bags/helmets/first aid kits back from coaches
relocate bags from South Side storage to Shaws Ln to Prepare them for inventory in Fall/Spring