## Work Items
Last Update | 2023-02-12
TASK |  |  |  | STATUS |  |  |  | EFFORT/COST
Item | Problem Area (Building/Fields/Facility/Equipment) | Problem Description | Corrective Action | Priority | When to Accomplish | Suggested Provider (Internal vs. Contractual) | Planned Year | Estimated Cost | Estimated Effort (Man-hours)
1 | Building | Access door to 2nd floor of 1st base dugout on Murray Field is deteriorated and continually vandalized. | At a minimum, replace door. Reconstruct media dugout and purchase security system at a maximum. | H |  | Contract |  | $500-$5K
2 | Facility | Lack of security system leads to increased possibility of vandalism to different structures at park | Purchase a security system to help with vandalism. | H | Anytime | Contract
3 | Fields | Outfields are uneven each spring and present injury hazard | Consider purchasing fill for divots to help level and roller to flatten and level each spring. | H | September/October | Contract | 2023
4 | Fields | Fencing is deteriorated and causes safety hazard to players | Replace 10' high fence between 1st base dugout and backstop on Gabarro Field | H |  | Contract
5 | Fields | Inadequate support behind backstop at Murray field doesn't prevent field erosion | Construct retaingin wall to hold and minimize field erosion issues. | H | Summer / Fall | Contract | 2023 | $20K | 360
6 | Fields | Outfield fencing posts on Murray Field have been pushed out of ground due to frost heaves and fence does not reach ground | Remove/replace apprx. 125' of posts in ground and rehang fencing | H
7 | Building | Underutilized storage facility on 2nd floor of concession bldg. | Enlarge existing team equipment storage lockers to include new shelving, etc. for just four - six teams on second floor of concessions building. | L |  | Volunteers
8 | Building | Access to 2nd floor media center of dugout on Murray field is hazardous as stairs are not per code. | Remove stairs and install new stairs with landing. | L
9 | Building | Training equipment is exposed to weather due to lack of space. | Construct small storage facility on existing concrete slab at Murray field to house just training equipment. Items such as pitching machine, cords, protective screens, etc. | L
10 | Equipment | Lack of hand tools impedes timely repair and maintenance of facility equipment | Purchase tool boxes and hand tools for both storage facilities at South Side. | L | Anytime | Director of Facilities | 2023 | 200 | 2
11 | Equipment | Current base system is old and poses potential safety hazard on Gabarro and Murray fields | Replace base systems | L | April | Equipment Mgr. |  | 750 | 4
12 | Facility | Gabarro Field garden needs to be enhanced. Upper garden is overgrown with weeds. | Purchase perennials for lower garden and add mulch. Remove old flowers/weeds and rebuild garden outside batting cage to include new shrubs, flowers and mulch. | L | Spring | Volunteers
13 | Facility | Bleachers (2) at Murray Field sit directly on grass which leads to weed growth below. | Move bleachers and groom area with landscaping timbers and mulch/wood chips underneath and replace bleachers. | L | July - Oct
14 | Fields | Frost heaves have caused breakdown of fence integrity by forcing posts out of ground.. Fencing no longer reaches ground level. | Reset fence posts and fencing of enclosure outside 3rd base dugout at Gabarro Field | L |  | Contract
15 | Fields | Need to have supply of loam and infield mix on hand to service fields when needed (see Item 20) | Purchase 2-3 yds of each material and store and property and cover with tarps. | L | Prior to season |  | 2023
16 | Fields | Warning tracks and areas inside fences in foul territory on both Gabarro and Murray fields are overgrown and need attention | Remove vegetation and install new cinder stone along fencing on both fields. | L
17 | Fields | Netting above 1st base fencing on Murray field is ripped, no longer attached and doesn't serve original purpose | Purchase and install new netting above 1st base fencing. UPDATE: Netting purchased in Aug21 and placed in upper storage building. | L | Anytime except winter

## Completed Tasks
TASK |  |  | STATUS |  |  | EFFORT/COST
Problem Area (Building/Fields/Facility/Equipment) | Problem Description | Corrective Action | Priority | When to Accomplish | Suggested Provider (Internal vs. Contractual) | Estimated Cost | Estimated Effort (Man-hours) | Actual Cost | Actual Effort (Man-hours) | Date Completed
Building | Old freezer in concession stand does not work | Removed door and brought freezer to recycling | L | Anytime | Volunteers |  | 1 | 20 | 2 | 2020-11-17
Facility | Existing memorial bench timbers are deteriorated | Removed rotting timbers and rebuilt with PT 4x4s around Adam Loudon Memorial granite bench | L | Jul.-Nov | Volunteers / Board members |  | 3 | 150 | 3 | 2020-10-05
Equipment | Old paints and sealers in concession bldg. storage are no longer usable | Dispose of items in trash or on Dover's Hazardous Waste Day @ Recycling Ctr. | L | August | Board Members |  | 1 | 0 | 1 | 2020-08-22
Building | Upper Storage building fascia board is deteriorated from carpenter bee damage | Replace fascia board on upper storage building. | L |  | Volunteers / Board members |  | 2 |  |  | 2020-08-08
Facility | Area around Red Murray monument needs to be cleaned/groomed from tree removal | Remove new growth, trim stumps. Add small plantings? | L | 2020 | Volunteers / Board members |  | 3 |  |  | 2020-07-18
Building | Murray Field 3rd base dugout soffits are deteriorated; have holes in them. | Cleaned, replaced damaged soffit, and replaced fascia board on 3rd base dugout. Needs to be painted. | L | July-November | Volunteers / Board members |  | 2 | 60 | 2 | 2020-07-13
Facility | Handicapped parking spaces are nearly invisible. | Repainted Handicap Parking spaces | L | 2020 | Volunteers / Board members |  | 2 | 20 | 2 | 2020-06-15
Fields | Previous fence post footing of left field gate access at Murray field is hazard | Remove fence post footing |  | July-November | Volunteer |  | 2 | 1 | 2 | 2020-06-01
Facility | Existing tree drops twigs, branches and seedlings on field | Cut down tree outside home plate at Murray Field |  | July-November | [5 empty] | 2019-10-19
Facility | Red Murray monument is not visible to public | Remove shrubs and trim plantings and reconstruct garden around Red Murray monument |  |  | Volunteers |  |  |  |  | 2019-10-19
Facility | Poor drainage on Gabarro Field during spring melt makes use of field uncertain for start of spring season | Replace drainage in outfield of Gabarro Field |  | July/August | Contracted Hillside (?) for work |  |  | 8450 |  | 2019-09-19
Facility | Each spring snow melt causes muddy ditch | Install crushed stone drainage in depression between road and Murray Field |  | 2019 | Contracted Wade Landscaping |  |  | 4000 |  | 2019-06-19
Building | Murray Field 3rd base dugout has been tagged with grafitti on inside walls | Painted Walls |  | 2020 | Volunteers / Board members |  | 1 | 20
Building | Concession building doors have graffiti on them | Concession Doors Panted |  | 2020 | Volunteers |  | 1 | 40
Equipment | Total amount of Field equipment is unknown | Field Equipment invnetory included as tab in this file | L | September/October |  |  | 3 | 0 | 3 | 2021-05-21
Building | Concession building exterior needs new paint to cover spot | Paint concession building |  |  | C |  | 160 | April-November | 160 | 2021-09-01
Building | Refrigerator in concession stand is not keeping beverages cold. | New refrigerator acquired |  |  | C |  | 160 |  | 160 | 2021-09-01
Building | Concession building fascia and peak paint is faded | Repainted concession building |  | April-November | C |  | 160 | April-November | 160 | 2021-09-01
Building | Old scoreboard on main concessions building does not work. | Old scoreboard removed by contractor |  | July-October | C |  | 160 | July-October | 160 | 2021-09-01
Building | Roof fascia board on main concessions building is deteriorated | Fascia board replaced |  | July-October | C |  | 160 | July-October | 160 | 2021-09-01
Building | Murray Field 3rd base dugout fascia board and new soffit needs to be painted. | Painted new fascia board. | L | April-November | Volunteers / Board members |  | 2022 | $0-Used existing paint | 1.5 | 2021-11-08
Building | Upper Storage building fascia board needs to be painted. | Painted new fascia board on upper storage building. | L | April-November |  |  | 2022 | $0-Used existing paint | 1.5 | 2021-11-08
Equipment | Pepsi fridge compressor in concession stand is noisy | Dispose of Pepsi fridge; bring to recycling. | L | 2022 |  |  |  | 0 | 2 | 2022-04-30
Facility | Park entrance sign is not entirely visible and some shrubs have died. | Remove dead shrubs/trees and trim others to make sign visible. New plantings should enhance area. | L | April-October | Volunteers / Board members | 100 |  | 0 | 3 | 2023-09-30

## Field Equipment Inventory
Location | Lower Storage Building |  | Notes | Location | Upper Storage Building |  | Notes
Item | Unit Issue | Quantity |  | Item | Unit Issue | Quantity
Screen Drag | Ea. | 1 | 4 ft. | Screen Drag | Ea. | 1 | 2 ft.
Aluminum Field Rakes | Ea. | 3 |  | Aluminum Field Rakes | Ea. | 3
Tamping tools | Ea. | 1 |  | Tamping tools | Ea. | 1
Batting Box Templates | Ea. | 1 |  | Batting Box Templates | Ea. | 2
Lime | Bag | 0.5 |  | Lime | Bag | 1
Turface | Bag |  |  | Turface | Bag | 1
Field Paint | Can | 3 |  | Field Paint | Can | 4
Puddle pads | Ea. | 2 |  | Puddle pads | Ea. | 2
Steel Garden Rakes | Ea. | 4 |  | Steel Garden Rakes | Ea. | 2
Leaf rakes | Ea. | 2 |  | Leaf rakes | Ea. | 1
Spades (Long-Handled | Ea. | 2 |  | Spades (Long-Handled | Ea. | 1
Spades (Short Handled) | Ea. | 2 |  | Spades (Short Handled) | Ea.
Shovels | Ea. | 3 |  | Shovels | Ea. | 1
Garden Hoe | Ea. |  |  | Garden Hoe | Ea. | 1
Pitchfork | Ea. | 2 |  | Pitchfork | Ea.
Weeding tool | Ea. | 1 |  | Weeding tool | Ea.
Lawn Edger | Ea. | 1 |  | Lawn Edger | Ea. | 1
Lawn Edger (Gas powered) | Ea. | 1 |  | Lawn Edger (Gas powered) | Ea.
Push Brooms | Ea. | 1 |  | Push Brooms | Ea. | 1
Kitchen Brooms | Ea. | 1 |  | Kitchen Brooms | Ea.
Extension Cords | Ea. | 1 |  | Extension Cords | Ea. | 4
Gas Cans | Ea. | 7
Paint Brushes | Ea.
Paint trays | Ea. |  |  | Blue Tarp | Ea. | 1
Step Ladders | Ea. | 2 |  | Step Ladders | Ea. | 1 | Wooden
Garden Sprayer (Manual) | Ea. | 1 |  | Extension Ladder (16 ft.) | Ea. | 1

## Items Needed (Budget)
Item | Location Needed | Supplier | Qty | Apprx. Cost (Each) | Total Cost | List of Various Suppliers
Field Equipment | [5 empty] | Amazon
Screen drag | Murray Field | M.A.S.A. | 1 | 250 | 250 | Beacon Athletics
Puddle pads | Both | M.A.S.A. | 2 | 90 | 180 | Mid-America Sports Advantage (M.A.S.A.)
Nail Drag Tines | South Side Fields |  |  |  | 0 | On Deck Sports
Field Roller |  |  |  |  | 0
0
0
0
0
0
0
Field Equipment (Subtotal) |  |  |  |  | 430
Training Equipment
7x7 Hitting Replacement Nets | South Side Fields | Mid-America Sports Advantage | 2 | 144.99 | 289.98
Jugs Instant Screen (Pup-Up Net) |  |  |  | 134.99 | 0
Hitting Sticks |  |  |  |  | 0
Pitching Machine Balls |  |  |  |  | 0
0
0
0
0
0
Training Equipment (Subtotal) |  |  |  |  | 289.98
Total |  |  |  |  | 719.98

## Sponsors Signs
South Side Fence Sign Sponsors |  |  |  |  | Shaw's Lane Fence Sign Sponsors
Business | Business Location (if not Dover) | Building Location (Lower/Upper) | Size (ft.) | Material (Metal/Poly/Corrugated Plastic) | Business | Business Location (if not Dover) | Building Location (Lower/Upper) | Size (ft.) | Material (Metal/Poly/Corrugated Plastic)
Berry/Jones Plumbing & Heating | Portsmouth | L | 3 x 4 | M
DF Richard |  | L | 3 x 4 | M
Dover Veterinary Hospital |  | L | 3 x 4 | M
Durell Paving |  | L | 3 x 4 | M
Durell Paving |  | L | 3 x 4 | M
Eastern Bank |  | L | 2 x 6 | P
Garrison Early Childhood |  | L | 3 x 4 | M
GC\AAA Fences |  | L | 3 x 4 | M
HBL Insurance |  | L | 2 x 6 | P
Infinite Imaging |  | L | 3 x 4 | M
K.C. Paving |  | L | 3 x 4 | M
K.C. Paving |  | L | 3 x 4 | M
Martel Plumbing |  | L | 3 x 4 | M
Martel Plumbing |  | L | 2 x 3 | M
Martineau Electric |  | L | 3 x 4 | M
Martineau Electrical Contr. |  | L | 3 x 4 | M
Middleton Building Supply |  | L | 3 x 4 | M
MR Motors | Eliot | L | 2 x 6 | P
Newburyport Bank |  | L | 2 x 6 | P
Newick's |  | L | 3 x 4 | M
Portsmouth Regional Hospital | Portsmouth | L | 2 x 6 | M
Power Pro Electrical Contr. | Portsmouth | L | 3 x 4 | M
R.W. Insurance |  | L | 3 x 4 | M
River Bend Pizza & Subs |  | L | 2 x 6 | P
River Bend Variety |  | L | 3 x 4 | M
Ross Furniture |  | L | 3 x 4 | M
Rotary International |  | L | 3 x 4 | M
Ryan's Tree Service |  | L | 2 x 6 | P
Sebastian Septic Service (Ronnie's Johnnies) | Milton | L | 3 x 4
Shaw's |  | L | 2 x 6 | M
Tasker Funeral Service |  | L | 3 x 4 | M
Tri-City Dodge |  | L | 3 x 4 | M
Tri-Tech Engineering Corp. |  | L | 3 x 4 | M
Tri-Tech Engineering Corp. |  | L | 3 x 4 | M
Weathervane Seafoods |  | L | 3 x 4 | P
Wentworth-Douglass Hospital |  | L | 3 x 4 | M
Women of the Moose |  | L | 2 x 6 | P
Asia Restaurant |  |  | 3 x 8 | M
Advanced Wildlife Control |  | U | 3 x 4 | P
Bellamy Watson Fields |  | U | 2 X 6 | P
Bill Dube Ford/Toyota |  | U | 3 x 4 | M
Ciotti Racing Products |  | U | 3 x 4 | M
Domino's Pizza |  | U | 3 x 4 | M
Dover Cyclery |  | U | 2 x 6 | M
Dover Police Association |  | U | 2 x 6 | M
Dover Police Charities |  | U | 2 x 6 | M
GC\AAA Fences |  | U | 3 x 4 | M
Green Grass Lawn Care |  | U | 2 X 6 | M
I.O.O. F. Lodge #3 (Weco Hamet) |  | U | 3 x 4 | M
Land Care Associates |  | U | 2 x 6 | P
Jewett Construction |  | U | 3 x 4 | M
Lenk Orthodontics |  | U | 2 x 6
Loyal Order Of Moose |  | U | 2 x 6
Meineke Car Care |  | U | 3 x 4 | M
My School |  | U | 3 x 4 | M
Olympia Sports |  | U | 3 x 4 | M
Orchard Title |  | U | 2 x 6 | P
O'Reilly Auto Parts |  | U | 2 X 6 | P
Red's Shoe Barn |  | U | 2 x 6
Richard W. Miller DDS |  | U | 2 x 6 | M
Seacoast Kettlebell |  | U | 2 x 6 | P
Sport & Spine Physical Therapy |  | U | 2 X 6 | P
Tri City Masonry & Tile |  | U | 3 x 4 | M
Tri-City Masonry Supplies |  | U | 3 x 4 | M
Wade Landscaping |  | U | 2 x 6 | P
Waste Management |  | U | 3 x 4 | M
WTSN AM 1270 |  | U | 3 x 4 | M
Wyskiel, Boc, Tillinghast & Bolduc |  | U | 2 x 6 | M
Wade Landscaping |  |  | Large